## Slide 1: Closeout

## Slide 2: Purpose
Prepare for Closeout.
Explain why Closeout matters.
Discuss the benefits of closing.
Review Closeout process.

## Slide 3: What is closeout?
Last administrative task.
Requirement.
Also assures you are fully reimbursed.

## Slide 4: Purpose of project closeout
To ensure:
  All physical work is complete.
  Final claim of all eligible costs are documented.
  Insurance proceeds are reconciled.
  Obtain and maintain requirements are met.
  Actual costs have been reimbursed.

## Slide 5: GOHSEP’s role in closeout
Protect reimbursement now and tomorrow
  OIG Audit

## Slide 6: Why closeout matters?
There are 3,598 large projects reporting as 100% complete.
Since work is done, FEMA requires projects to be closed.

## Slide 7: Required closeout metrics
DISASTERS | 2014-15 LARGE PWS | 2014-15 SMALL PWS
Katrina/Rita | 1,200 | 10,072
Gustav/Ike | 648 | 1,704
Other Disasters | 119 | 193
Totals | 1,967 | 11,969

## Slide 8: Why closeout matters?
If GOHSEP does not meet closeout metrics:
  State Management Costs may not be extended.
    GOHSEP is advocate for you and the citizens.
  Closeout Incentive will not be extended.

## Slide 9: Gustav/Ike closeout deadline
September 2016
Gustav/Ike
Closeout Deadline

## Slide 10: Benefits of closing a project
Subrecipient (Applicants) may receive additional payments.
Subrecipient (Applicants) do not have to complete a Quarterly Report for closed projects.
You can go back to your day job.

## Slide 11: When is project ready to close?
Work has been completed.
No versions currently in process.
No outstanding appeals or arbitrations.
No pending reimbursement requests.

## Slide 12: Types of closeouts
Grouped (Preferred)
Large
Insurance
Actual Cost
Certification
Certification
Single
Estimates
Small

## Slide 13: Small projects: Closeout exceptions
Small project “netting”
  Request additional funding for all small projects.
  Supporting documentation for netted small projects reviewed same as large projects.

## Slide 14: Small project netting
Project Number | Current Obligation | Actual Costs | Variance
Project 1 | $10,000.00 | $5,000.00 | ($5,000.00)
Project 2 | $10,000.00 | $20,000.00 | $10,000.00
Totals | $20,000.00 | $25,000.00 | $5000.00
Net is $5,000.00

## Slide 15: Large project closeout
Submit Closeout Request

## Slide 16: Large project closeout
Submit Closeout Request
State Preliminary Review

## Slide 17: Large project closeout
Submit Closeout Request
State Preliminary Review
Missing Documents

## Slide 18: Large project closeout
Submit Closeout Request
Final Reconciliation Completed
State Preliminary Review
Missing Documents

## Slide 19: Large project closeout
Submit Closeout Request
Final Reconciliation Completed
FEMA Reviews Closeout Packet
State Preliminary Review
Missing Documents

## Slide 20: Large project closeout
Submit Closeout Request
Final Reconciliation Completed
FEMA Reviews Closeout Packet
Final Financial Transactions Completed
State Preliminary Review
Missing Documents

## Slide 21: Additional documentations during closeout
Proof of payment (Vendors)
Insurance Statement of Loss
Proof of insurance O + M requirements

## Slide 22: Additional documentations during closeout
Proof of compliance with EHP requirements
Site Inspections Reports

## Slide 23: Additional documentations during closeout (Closeout . . . )
TIP: Banks have a limited retention requirement of your records.
It is important that you request copies of bank statements.

## Slide 24: Documentation retention
Once closed, still subject to audit.
Recommendation to maintain electronic files.

## Slide 25: Documentation retention (Continued . . . )
  LouisianaPA.com is a useful storage platform.

## Slide 26: Closeout funding
Closeout Incentives (COI) for Katrina/Rita
  Subgrantees may claim up-to 3% of eligible project costs.
  Hours tracked to eligible tasks for specific project.
  Reasonable cost.

## Slide 27: Closeout funding (Continued . . . )
Direct Administrative Costs (DAC) disasters post November 13, 2007 for Closeout.
  Hours tracked to eligible tasks for specific project.
  Reasonable cost.

## Slide 29: Closeout contacts
Nathan Elkins
Group Lead – Katrina/Rita
  (225) 339-3723
  nathan.elkins@la.gov
Public Assistance Main Line
  (225) 346-4112
  Kennon Clayton
  Group Lead – All Other Disasters
  (225) 242-6014
  kennon.clayton@la.gov
Christina Knighten
Section Chief
  (225) 338-6763
  christina.knighten@la.gov

## Slide 30
Questions?