Hurricane Delta – State/EMAC Demobilization Plan

Date/Time Prepared

10/8/2020 2000

| Name |  | Title | Signature |
| --- | --- | --- | --- |
| Prepared By | Julie McCabe | LA IST DPSC |  |
| Approved By | Anita Arnum | Blue IST Demob |  |
| Approved By | Austin Davis | Finance Section Chief |  |
| Approved By | Gregory Davis | Plans Section Chief |  |
| Approved By | Chad Roberson | Operations Section Chief |  |
| Approved By | Kyle Percy | Logistics Section Chief |  |
| Approved By | Traci Travis | Safety Officer |  |
| Approved By | Ruel Douvillier | ISTL |  |
| Final Approval | Dan Wallis | Incident Commander |  |

DRAFT

The Louisiana Demobilization Plan contains four (4) sections:

- General Information

- Responsibilities

- Release Procedures

- Travel Information

- GENERAL INFORMATION

The demobilization process will require coordination with the Incident Commander.

All releases from will be initiated in the Planning Section after Incident Commander approval. No resources are to leave the Incident until authorized to do so. At this time, demobilization will be conducted remotely to decrease the potential spread of COVID-19 with limited resources completing on-site demobilization at:

7979 Independence Blvd.

Baton Rouge, LA 70806

# RESPONSIBILITIES

The Incident Commander is responsible for:

  - Establishing the release priorities.

  - Reviewing and approving the Demobilization Plan.

The Safety Officer is responsible for identifying any unaddressed issues with the demobilization plan and travel plans as they submitted.

DRAFT

The Operations Section is responsible for:

  - Provide the Planning and Logistics section a list of resources declared excess at least 24 hours prior to estimated departure.

  - Information on Critical Incident Stress Management for all responders, if needed, is provided prior to departure.

  - Make sure all Operational Resources turn in Travel Plans to the Demob Unit in Planning.

The Planning Section is responsible for:

  - Collect all ICS 214 unit logs, accident/damage reports with pictures, travel plans.

  - Making sure that all signatures are obtained on the Demobilization Checkout Form ICS 221.

  - Monitoring the Demobilization process and making any adjustments in the process.

The Logistics Section is responsible for ensuring the following:

  - Facilities—that ICP is cleaned up before personnel are released.

  - S

upply—that all non-expendable property items are returned or accounted for

prior to release.

  - G

round Support—that accidents and damage to equipment is reported to Logs;

SF91 “Motor Vehicle

pictures of any accidents and damage are submitted with the

Accident Report” and attach supporting documentation

  - C

ommunications—that all radios have been returned or are accounted for.

The Finance Section is responsible for:

  - Completion of all time and equipment reports for released personnel.

The Planning Section will be the last stop in the release process!

# RELEASE PROCEDURES

The Incident Commander will notify all Command and General Staff of release time. Each individual will submit the ICS Form 221, Demobilization Check-Out form, to:

sfmdispatch@gmail.com

The following are general guidelines to be followed for resources leaving the Incident.

  - Transportation to original departure point shall be the responsibility of the home agency.

DRAFT

Departing resources must meet individual agency regulations pertaining to rest and travel.

  - All equipment used during operations shall be properly decontaminated before departure.

  - Task Force leaders, Strike Team Leaders, and any other positions with subordinates must make sure there is a proper transportation plan in place, to include driving plan (passengers and/or vehicle stops if needed, etc.). A proper vehicle check prior to demobilization shall take place.

Upon verification from all sections, a returned ICS Form 221 will be emailed back to the Task Force or single resource as acknowledgement that the Demob process is complete and units may begin movement to their home of record.

# TRAVEL INFORMATION

- Released Resources shall follow Demob plan procedures. All drivers will meet agency work/rest requirements prior to being released from the incident.

- No person(s) will be released without having a MINIMUM of 1 2 hours rest for any drivers. Exceptions granted by the Incident Commander based on travel times and distances.

- Released personnel shall not travel more ten (10) hours (drive time) a day and shall reach their home base prior to 2200 hours (10pm).