## Slide 1: Unit 3
The All-Hazards Planning Cycle
USFA Type 3
All-Hazards Incident Management Team Introduction

## Slide 2: Unit Objectives
Identify components of the All-Hazards Planning Cycle.
Respond to leadership challenges within the context of an incident.
Identify characteristics of Specific, Measurable, Action-oriented, Realistic and Time-sensitive (SMART) Objectives.
Identify the purpose of the meetings and briefings in the All-Hazards Planning Cycle.

## Slide 3: Unit Objectives
Identify and perform the major processes involved in Strategy, Tactics, Planning Meetings, and an Operational Period Briefing.

## Slide 4: Incident Action Planning Process
Five phases:
  Understand the situation.
  Establish Incident Objectives, strategies, and tactics.
  Develop the plan.
  Disseminate the plan.
  Execute, evaluate, and if necessary, revise the plan.

## Slide 5: Incident Action Planning Process
Is central to managing incidents.
Culminates with the completion of an Incident Action Plan (IAP).
Contains sequential steps.
Is repeated every Operational Period.

## Slide 6: Planning P
Planning P
National Incident Management System (NIMS) third edition
October 2017.

## Slide 7: Planning Cycle Comparison
All-Hazards Planning Cycle
NIMS Planning Cycle

## Slide 8: What Is the All-Hazards Planning Cycle?
Represented by the All-Hazards Planning P.
A standardized approach to organizing the operational cycle.
    Indicates which meetings/briefings to conduct.
    Indicates which Incident Command System (ICS) forms/worksheets to complete.
    Outlines each All-Hazards Incident Management Team (AHIMT) member’s action/products.

## Slide 9: Operational Period
The repetitive part of the All-Hazards Planning Cycle.
Meeting schedule is based on length of Operational Periods.
Contains three meetings, one briefing and several blocks of time.

## Slide 10
See At a Glance #1
Core Concepts

## Slide 11: Stem of the Planning P
Begins when Incident/Threat occurs.
After Notification, the AHIMT responds, conducting an assessment while en route and upon arrival.
After gathering information, the AHIMT meets with the Agency Administrator (AA) (if appropriate) and Initial Response IC (ICS 201 Briefing).
See At a Glance #2
Initial Response

## Slide 12: Transfer of Command
Category of Transfer of Command:
    From initial response.
    Team-to-team.
    Team to a higher-capability IMT.
    Team back to local authority.
May be assigned a management or support role.
Must not affect safety or productivity.
Most successful where a shadow period is included.

## Slide 13
0400
1000
1800
Incident
Start
AHIMT
Incorporated Into Incident Management
Resources Managed
By OSC
TRANSITION
1700 OPERATIONAL PERIOD BRIEFING
Managed by 1st Responders
IAP’s Guiding Document
ICS 201 is the Guiding Document
Incident Timeline (from Initial Response)
Operational Period Begins

## Slide 14: Agency Administrator Briefing
Necessary when the Incident Command (IC) assumes incident management duties outside normal position description or is from a jurisdiction that doesn’t possess authority to manage the incident.
Used to convey critical information needed to achieve management's goals.

## Slide 15: Agency Administrator Briefing
The incoming AHIMT first briefing
      Find out details of incident.
      Briefed on Agency Administrator’s (AA) intentions, restrictions (leader’s intent).
      Delegation of Authority (DoA).
      Team role (management or support).
      Political considerations the team needs to be aware of (back story).
See At a Glance #3
Agency Administrator Briefing

## Slide 16: Incident Briefing ICS 201
The ICS 201 Incident Briefing contains overview information about the incident.
Used as a briefing tool.
Provides information on:
  Map/Sketch (area of responsibility).
  Situation Summary and Health and Safety Briefing.
  Current and Planned Objectives.
  Current and Planned Actions, Strategies and Tactics.
  Current Organization.
  Resources Summary (assigned and en route).

## Slide 17: Incident Briefing-Considerations
The AHIMT receives the incident briefing from the current IC or Operations Section Chief (OSC).
Used to assess the situation.
Assist the Team in evaluating and validating the incident situation vs. the Incident Briefing.
See At a Glance #4
Incident Briefing

## Slide 18: Initial UC Meeting (If Unified Command)
Is necessary when in Unified Command (UC).
Provides the ICs the opportunity to discuss and concur on important issues.
Documents decisions and directions.
See At a Glance #5
Initial UC Meeting

## Slide 19: Early Leadership Challenges
Lines of authority.
Accountability Procedures.
Delegation of Authority.
Personnel relief and rehabilitation.
Situational awareness.
Environmental considerations.
Evacuations.
Financial constraints.
Incident-within-an-incident.
AHIMTs need to recognize sensitive political, legal, and security issues.

## Slide 20: Activity 3-1: Responding to Leadership Challenges
Total Time: 30 minutes
10 min. | Using the list of Issues/Concerns from Activity 2-1 teams will work together to select two issues to be addressed.
10 min. | Teams will propose strategies to address each selected issue.
10 min. | Teams will present their strategies for each selected issue to the rest of the class.

## Slide 21: IC/UC Sets Initial Incident Objectives
Develop Incident Objectives within the scope of the DoA.
Take into consideration Incident Priorities, strategies, limitations, concerns, and constraints.
See At a Glance #6
IC/UC Sets Initial Incident Objectives

## Slide 22: Setting Objectives
Set by the IC (or UC if Unified Command)
Follows the SMART format
  Specific - is the wording precise and unambiguous?
  Measurable - How will achievements be measured?
  Action-oriented - Is an action verb used to describe expected accomplishments?
  Realistic - Is the outcome achievable with given available resources?
  Time-sensitive - What is the timeframe? (if applicable)

## Slide 23: Operational vs. Management
Objectives can be categorized as Operational or Management Objectives.
Operational Objectives will need to be addressed in the tactical plan using the ICS 215 Operational Planning Worksheet.
Management Objectives are usually addressed by other AHIMT members.

## Slide 24: Operational vs. Management Objectives
Operational Objectives
Provide protection of environmentally sensitive areas, including wildlife, and historic properties throughout the incident.
Initiate actions to control the source of the leak and minimize the volume released by 1300 hours.
Management Objectives
Keep the public, stakeholders, and elected officials informed of operational activities throughout the incident.
Ensure that appropriate financial accounting practices are established by 1300 hours.

## Slide 25: SMART Objectives Example 1 of 3
Is this statement
  Specific?
  Measurable?
  Action-oriented?
  Realistic?
  Time-sensitive?
“Get the situation under control.”

## Slide 26: SMART Objectives Example 2 of 3
Is this statement
  Specific?
  Measurable?
  Action-oriented?
  Realistic?
  Time-sensitive?
“Establish a secure perimeter as soon as possible and maintain perimeter control throughout the incident.”

## Slide 27: SMART Objectives Example 3 of 3
Is this statement
  Specific?
  Measurable?
  Action-oriented?
  Realistic?
  Time-sensitive?
“Establish a medical treatment group to provide medical care for victims throughout the incident.”

## Slide 28: Activity 3-2: Developing Incident Objectives
Total Time: 55 minutes
45 min. | Using the list of Issues/Concerns developed in Activity 2-1, and completed ICS 201 as a reference: Develop SMART Incident Objectives on an easel pad. Determine whether the Objective is an Operational or Management Objective.
10 min. | Each team’s spokesperson will report out their Incident Objectives.

## Slide 29: Initial Strategy Meeting and Information Sharing – Purpose
Communicate priorities, Incident Objectives.
Discuss the Strategies to be used to meet the Incident Objectives.
Discuss issues observed during transition.
Establish Operational Periods.
Establish the Planning Cycle meeting and briefing schedule.
Communicate additional resource needs.
See
At A Glance #7
Initial Strategy Meeting

## Slide 30: Initial Strategy Meeting and Information Sharing – Considerations
May be facilitated by the Planning Section Chief (PSC).
Provides the first opportunity of the Command and General Staff to share critical incident information.
Makes specific assignment to AHIMT members for tasks not included in normal duties.

## Slide 31: Initial Strategy Meeting and Information Sharing – Actions
Share concerns, assessments, and observations necessary for the AHIMT to form a Common Operating Picture (COP).
Describe resource ordering procedure.
Clarify issues and/or concerns.
Share information.

## Slide 32: Operational Period- Considerations
Safety concerns, unsafe conditions.
Conditions of resources.
Length of time necessary or available to achieve the tactical assignments.
Availability of resources.
Future involvement of additional jurisdictions or agencies.
Environmental conditions.
Planned event schedule.

## Slide 33: Operational Period Examples
Dawn to Dusk
Often used if only working during the daylight hours.
Risk versus reward; safety concerns.
No life safety, e.g. Recovery mission.
12-hour Operational Periods
Two 12-hour Operational Periods; one during the day, one at night enabling continuous work.
Life safety, e.g. missing person.
Often 0600-1800 hrs., 1800-0600 hrs.

## Slide 34: Planning Cycle Meeting Schedule
Developed by the PSC after discussion with the OSC, LSC and IC/UC.
Approved by the IC/UC.
PSC works backward from the start of the Operational Period.
Allow time to accomplish each step.

## Slide 35
0600 – Day Operational Period to begin
2200
0500
2100
2000
1900
Sample Meeting Schedule for a 12-hour Day Operational Period
Occurs after the previous Operational Period ended. Results may affect next Operational Period

## Slide 36
1800 – Night Operational Period to begin
1300
1700
1100
0800
0700
Sample Meeting Schedule for a 12-hour Night Operational Period
Occurs after the previous Operational Period ended. Results may affect next Operational Period

## Slide 37: Operations Section-Organizational Elements
Single Resource – an individual, equipment, personnel, crew or team.
Strike Team/Resource Team – same kind and type of resources.
Task Force – a combination of single resources.
Division – divides an incident into geographical areas.
Group – divides an incident into functions.
Branch – found between Operations Section Chief and Divisions/Groups (can be functional or geographic).

## Slide 38: Preparing for the Tactics Meeting
This is a block of time, not a meeting:
  OSC consults with section personnel to determine current situation, progress.
  OSC documents proposed work assignments and required resources using the ICS 215.

## Slide 39: Preparing for the Tactics Meeting
Identify the strategy and tactics needed to meet the Operational Incident Objectives.
Address all the Operational Objectives should be addressed on the ICS 215.
Develop the organization, work assignments, and required resources.

## Slide 40: Preparing for the Tactics Meeting
Logistics Section Chief (LSC) assesses logistical support capabilities.
PSC determines resource availability, what displays, projections, etc. the OSC requires.
Safety Officer (SOF) identifies/updates the hazards/risks and mitigation measures.
See At a Glance #8
Preparing for the Tactics Meeting

## Slide 41: Preparing for the Tactics Meeting
Prior to the Tactics Meeting, the OSC should have:
  Operational Incident Objectives.
  Map (large enough to draw boundaries).
  Wire chart (Divisions/Groups/Branches).
  ICS 215 Operational Planning Worksheet.
  ICS 215A IAP Safety Analysis being completed by the SOF.

## Slide 42: Prior to the Tactics Meeting
  Set the incident perimeter.
  Create work assignments to address Objectives.
  Determine required resources (kind/type) and overhead.
  Build the organization within span-of-control limits.
  Review the map/chart to identify boundaries (Division/Branch).
  Determine Staging Area location(s), Drop Points, Helispots, etc.

## Slide 43: Tactics Meeting – Purpose
OSC communicates and establishes support for Draft Tactical Plan from a small group:
  SOF.
  LSC.
  PSC (Resources Unit Leader (RESL) if staffed).
  Others by invitation only.
See At a Glance #9
Tactics Meeting

## Slide 44: Tactics Meeting – Actions
OSC completes/presents the ICS 215 Operational Planning Worksheet.
SOF completes/presents the ICS 215A Incident Action Plan Safety Analysis.

## Slide 45: Relationship Between ICS 215 and ICS 215A
ICS 215A
ICS 215
Gives direction on which resources (quantity, kind, type) to be deployed and their work assignment to meet the Incident Objectives.
Identifies safety hazards/risks faced by these resources and mitigation strategies to be employed.
Resource and assignment data

## Slide 46: Activity 3-3: ICS 215 and 215A Demonstration
Total Time: 45 minutes
45 min. | Instructors will demonstrate how to complete ICS Forms 215 and 215A.

## Slide 47
A
ICS-215
Total Resources Required
Total Resources Have on Hand
Total Resources
Need to Order
Single
Resources
Single
Resources
Single
Resources
Strike
Teams
Strike
Teams
Strike
Teams
Req.
Have
Need
Req.
Have
Need
Req.
Have
Need
Req.
Have
Need
Req.
Have
Need
Req.
Have
Need
Req.
Have
Need
Req.
Have
Need
Req.
Have
Need
Req.
Have
Need
Req.
Have
Need
OPERATIONAL PLANNING WORKSHEET (215)
1. Incident Name
Date To:
Time To:
2. Operational Period : Date From:
Time From:
4 Division, Group,
or Other
5. Work Assignment & Special Instructions
6. Resources
7. Overhead
Position(s)
8.Special
Equipment &
Supplies
9. Reporting
Location
10. Requested
Arrival Time
11.
Jefferson County Haz-Mat
DP 1
Improve dikes around the spill area and below the road. Vacuum diazinon & diesel from roadway. Remove absorbent sand . Remove the contaminated soil and transfer remaining chemical to transport container and removal truck.
1800
1 1 2 1 1 2
3. Branch
14. Prepared By:
Name:_____Rich Olson____________
Position/ Title: OSC_______________
Signature:__________________________
Date/Time:___8/14 1300_____________
12.
13.
1
T-2 Dump Trk
T-3 Dozer
VacTrk, HZMT
P/U Trk, 1-Ton
T-1 Engine
8/14
1800
8/15
0600
H.D Tow Trk
1
2
1
1
2
DIVS
ASO-HM
Sand, 2-tons
75-Traffic cones
Rich Olson

## Slide 48
Jefferson County Haz-Mat
8/14
1800
8/15
0600
8/14 1130
Division A
Working with Hazardous Waste/ Exposure to Hazardous material could expose you to long term injury, or possible death.
Working around heavy equipment/ Injury or death
Division A
Division A
Working around moving traffic/Injury or death
All personnel will wear appropriate PPE for the operation as required by NIOSH guidelines and agency policy. Follow accepted protocol for proper disposal of used PPE
Be alert for heavy equipment movement; stay in view of the equipment operator ; wear high visibility vests and clothing; Use lighting
Maintain situational awareness; place traffic barriers in proper locations; wear high visibility vests and clothing
VA-FAX-1101
Jon Olney
8/14, 1130 hrs
Jon Olney

## Slide 49: Activity 3-4: Tactics Meeting Simulation
Total Time: 1 hour 45 min.
1 hour, 30 min. | Teams will work in their breakout rooms to complete ICS Forms 215 and 215A as part of a practice Tactics Meeting.
15 min. | The Instructor will debrief the activity.

## Slide 50
Operations requires a resource
OSC (or RESL) completes the ICS 213 General Message Form
OSC sends ICS 213 to Logistics Section
LSC places order with ordering point (EOC)
EOC fills order with resource requested
Resource checks in
with Planning Section
PSC lets OSC, LSC and FSC know the resource has checked into the Incident
Resource is assigned as directed by the OSC

## Slide 51: Preparing for the Planning Meeting
This is a block of time.
IC/UC meets informally with members or stakeholders as necessary.
OSC prepares ongoing update on current operations.
PSC assists setting up the meeting room and visual displays.
See At a Glance #10 Preparing for the Planning Meeting

## Slide 52: Preparing for the Planning Meeting
LSC verifies support requirements.
The IC and Command and General Staff should exchange information about the proposed plan.
If possible, conflicts should be resolved or mitigated prior to the meeting.

## Slide 53: Planning Meeting – Purpose
OSC presents the Draft Tactical Plan and PSC solicits support for the proposed plan from the Command and General Staff and approval of the IC/UC.
See At a Glance #11
Planning Meeting

## Slide 54: Planning Meeting – Considerations
Final opportunity for the Command and General Staff to hear the proposed plan and provide input.
All Operational Objectives must be addressed by the proposed work assignments/organization.
Logistical support is adequate.
Hazards/Risks are identified and mitigated.
Meeting is documented.
Financial and administrative reporting requirements are met.

## Slide 55: Planning Meeting – Actions
OSC presents ICS 215.
SOF presents ICS 215A.
Team develops alternative plans if necessary.
Team shares critical information.
Team members indicate support of the proposed plan.
IC/UC approves the plan.

## Slide 56: Activity 3-5: Planning Meeting Simulation
Total Time: 1 hour
1 hour | Teams will work in their breakout rooms to conduct a Planning Meeting (using the Planning Meeting Agenda as a guide) Rooms will be organized for the meeting with necessary displays, maps, and agenda posted.

## Slide 57: IAP Preparation and Approval
This is a block of time where the details and documentation of the IAP are completed.
Components of the IAP are delivered to the Planning Section to the location and time frame determined by the PSC.
The IAP is assembled by the Planning Section.
See At a Glance #12
IAP Preparation Approval

## Slide 58: IAP Preparation and Approval
After the PSC reviews it, the IAP is delivered to the IC/UC for review and approval.
IC/UC reviews and signs the IAP.
The approved IAP is then duplicated for distribution at the Operational Period Briefing.

## Slide 59: ICS Form Relationship: ICS 215, ICS 215A, ICS 205, and ICS 204
ICS 215 - Contains information on resources (quantity, kind, type) and work assignment.
ICS 215A - Hazards/Risks identification and mitigation.
ICS 205 Incident Radio Communication Plan - Communication methods.
ICS 204 Assignment List - Identifies specific resources and includes assignments, safety information, special instruction and communication methods.
Resource data

## Slide 60
COMMAND EMPHASIS
(IC)
ISSUES
CONCERNS
PRIORITIES
(Command and General Staff )
OBJECTIVES
(IC, PSC)
ICS 215
(OSC, RESL,
LSC)
ICS
215A
(SOF)
ICS
203
(RESL)
ICS
205
(LSC)
ICS
208
(SOF)
ICS
202
(IC, PSC)
Color Key Indicates
ICS Form or Team Member
Providing Information for Completion.

## Slide 61
COMMAND EMPHASIS
(IC)
ISSUES
CONCERNS
PRIORITIES
(C&GS)
OBJECTIVES
(IC, PSC)
ICS 215
(OSC, RESL,
LSC)
ICS
215A
(SOF)
ICS
203
(RESL)
ICS
205
(LSC)
ICS
208
(SOF)
ICS
202
(IC, PSC)
OPERATIONAL PERIOD DEFINED
CONTENTS BLOCK AND APPROVALS
ICS 202
ISSUES
CONCERNS
PRIORITIES
(Command and General Staff )

## Slide 62
COMMAND EMPHASIS
(IC)
ISSUES
CONCERNS
PRIORITIES
(C&GS)
OBJECTIVES
(IC, PSC)
ICS 215
(OSC, RESL,
LSC)
ICS
215A
(SOF)
ICS
203
(RESL)
ICS
205
(LSC)
ICS
208
(SOF)
ICS
202
(IC, PSC)
ICS 203
TABULAR
ORGANIZATION
CHART
From the Resource Tracking System used such as ICS 211-Check-in Lists,
T Cards, etc.
OPERATIONAL PERIOD DEFINED
APPROVALS BLOCK
ISSUES
CONCERNS
PRIORITIES
(Command and General Staff )

## Slide 63
COMMAND EMPHASIS
(IC)
ISSUES
CONCERNS
PRIORITIES
(C&GS)
OBJECTIVES
(IC, PSC)
ICS 215
(OSC, RESL,
LSC)
ICS
215A
(SOF)
ICS
203
(RESL)
ICS
205
(LSC)
ICS
208
(SOF)
ICS
202
(IC, PSC)
ICS 204
OPERATIONAL PERIOD DEFINED
APPROVALS BLOCK
Resource Identifier, Leaders’ name and information
(From 211 & T-CARDS)
ISSUES
CONCERNS
PRIORITIES
(Command and General Staff )

## Slide 64: Activity 3-6: Demonstration ICS Forms 203 and 204
Total Time: 30 minutes
30 min. | The Instructors will demonstrate information transfer to the ICS 203 Organization Assignment List and ICS 204 Assignment List.

## Slide 65
Jefferson County Haz-Mat
8/14
1800
8/15
0600
Rich Olson
A
Ronnie Hamm
Katie Magin
RESL
Katie Magin
8/14 1435 hours

## Slide 66
Jefferson County Haz-Mat
8/14
1800
8/15
0600
A
Improve dikes around the spill area and below the road. Vacuum diazinon & diesel from roadway. Remove absorbent sand. Remove the contaminated soil and transfer remaining chemical to transport container and removal truck.
Wrecker will be released from incident as soon as it removes truck from the scene. The truck will be delivered to the transport company.
Rich Olson 555-512-1212
Fairfax Eng. 2102
Ray Holbrook
5
555-512-1111
DP-1 1800
Fairfax Dozer 1
Regina Smith
1
555-512-1001
DP-1 1800
Fairfax Dump 1
Fairfax Dump 2
Ronnie Hamm 555-512-1313
Kevin Harrelson
1
555-512-1222
DP-1 1800
Mary Williams
1
555-512-1232
DP-1 1800
Grey’s Vac Truck #30
Joe Calvert
2
555-512-3332
DP-1 1800
Fairfax P/U #76
Alan Moffett
1
555-512-1234
DP-1 1800
Corey’s Tow Srv #121
Fran Varner
1
555-512-2233
DP-1 1800
ASO-HM
Brian Shield
1
555-512-7777
DP-1 1800
Motorola Jeff. Co.
Tactical Channel 1 - 154.280
Motorola Jeff. Co.
Command Channel 5 - 152.875
Katie Magin
RESL
Personnel working near water must wear PFD; appropriate PPE for Haz-Waste operation required, proper disposal of contaminated PPE; Watch for heavy equipment movement; situational awareness of deteriorating weather conditions; Provide appropriate work/rest periods
8/14 1400
Katie Magin

## Slide 67: ICS 205 Incident Radio Communication Plan
Completed by the Communications Unit (COML) Leader or LSC if COML unstaffed.
Outlines how the responders will communicate on the incident.

## Slide 68: ICS 206 Medical Plan
Completed by the Medical Unit Leader (MEDL) or LSC if MEDL is unstaffed.
Approved by the SOF.
Outlines Special Medical Emergency Procedures for responders.
Many jurisdictions and agencies have specific protocols and procedures.

## Slide 69: Special Medical Emergency Procedures (ICS 206 block 6)
In the event of a medical emergency, provide the following information:
Declare the nature of the emergency.
  Medical injury/illness? Life-Threatening?
If life-threatening, request frequency be cleared for emergency traffic.
Identify the on-scene point of contact (POC) by resource and last name.
Identify nature of incident, number injured, location patient assessment(s).

## Slide 70: Special Medical Emergency Procedures (ICS 206 block 6)
Identify on-scene medical personnel by position and name.
Identify preferred method of patient transport.
Request additional resources/equipment.
Document all information received/transmitted on the radio/phone.
As they occur, POC identifies any changes in:
    On-scene POC or medical personnel.
    Patient status.
    Situation.

## Slide 71: ICS 208 Safety Message/Plan
Completed by the SOF.
Addresses an issue the SOF would like to highlight.
The message often changes from one Operational Period to the next.
Bullet items work best.

## Slide 72: Operational Period Briefing – Purpose
Command and General Staff communicate details of IAP to Tactical Supervisors and representatives of supporting and cooperating agencies.
Should be short—it’s called a “briefing” for a reason!
See At a Glance #13
Operational Period Briefing

## Slide 73: Operational Period Briefing – Actions
Presentations by the Command and General Staff and select Unit Leaders.
Highlights important components of the IAP.
Focused, relevant, and directed toward Operations Supervisory personnel.

## Slide 74: Begin the Operational Period – Actions
Resources travel to their assigned location.
Starts with a face-to-face briefing from the individual being relieved.
Operational resources begin the task of implementing their portion of the IAP.
Specific tasks are assigned to individuals and individual resources as appropriate.
See At a Glance #14
Begin the Operational Period

## Slide 75: Execute Plan and Assess Progress
This is a block of time.
Resources execute their assigned portion of the tactical plan and note and report their progress in completing their assigned tasks.
This progress and recommended changes in actions or resources (kind/type, quantity) are passed on to the next level of supervision.
These recommendations are then incorporated into the planning process for the next Operational Period.
See At a Glance #15
Execute Plan and Assess Progress

## Slide 76: Execute Plan and Assess Progress - Actions
After the Operational Period change the off-going supervisors are interviewed to validate the IAP’s effectiveness.
Command and General Staff members each evaluate progress and make recommendations.

## Slide 77: IC/UC Validate or Adjust the Objectives
Based on input from the Command and General Staff particularly the OSC, the IC/UC will determine if the Objectives need to be modified or altered.
If needed, the IC/UC will draft the changes.
The PSC may facilitate this discussion.
See At a Glance #16
IC/UC Validate or Adjust the Objectives

## Slide 78: Strategy Meeting (If Objectives Adjusted)
A Strategy Meeting must be scheduled if the IC/UC adjust/modify the Incident Objectives.
Meeting should occur as soon as practical after the Incident Objectives have been adjusted.

## Slide 79: Strategy Meeting – Actions
Present the revised Incident Objectives and/or new strategies.
Evaluate Operational Periods/Meeting Schedule.
Discuss limitations, issues and concerns.
See At a Glance #17
Strategy Meeting

## Slide 80: Preparing for the Tactics Meeting
Start the planning cycle once again.
Adjust the plan as needed.
The AHIMT continues to enhance their COP.
OSC continues gathering updated incident information.
The Draft Tactical Plan must reflect any changes to the Incident Objectives.

## Slide 81: Additional/Optional Meetings
Command and General Staff Meetings.
Section Meetings.
Public Meetings.
Stakeholder Meetings.
Transition Meeting.
Team Closeout Meeting.
Team Debriefing Meeting.

## Slide 82: Activity 3-7: IAP Preparation and Operational Period Briefing
Total Time: 2 hours 15 minutes
1 hour 30 min. | Teams will work in their breakout rooms to complete ICS Forms and other items included in the IAPs.
25 min. | Mentors will review the teams’ IAP and offer feedback.
20 min. | Teams will practice an Operational Period Briefing in their breakout rooms.

## Slide 83: Activity 3-8: Cypress Tornado
4 hours 30 min. | Teams will work in their breakout rooms to manage the incident, prepare an IAP, and conduct an Operational Period Briefing.
 | Mentors manage the simulation distribution injects and monitor the team's response to the injects.
30 min. | Mentors will review the team’s IAPs and offer feedback.
30 min. | Teams will practice an Operational Period Briefing.
30 min. | One or more teams will be selected to demonstrate the Operational Period Briefing to the rest of the class.
Total Time: 6 hours 00 minutes

## Slide 84: Objectives Review
Identify components of the All-Hazards Planning Cycle.
Respond to leadership challenges within the context of an incident.
Identify characteristics of Specific, Measurable, Action-oriented, Realistic and Time-sensitive (SMART) Objectives.
Identify the purpose of the meetings and briefings in the All-Hazards Planning Cycle.

## Slide 85: Objectives Review
Identify and perform the major processes involved in Strategy, Tactics, Planning Meetings, and an Operational Period Briefing.