## Slide 1: L.W.I.N.
Louisiana Wireless Information Network
System Management & Maintenance October 23, 2024
Department of Public Safety
Office of State Police
Mobility and Communication Services
(225) 925-6036

## Slide 2: Infrastructure Update

## Slide 3: SYSTEM SUMMARY
150 Total Tower Sites in Operation
6 Operational Mobile Sites

## Slide 4
Pan Am
Bridge City
Livonia
Laplace
St. Tammany Simulcast
Lacombe
Abita Springs
Waldheim
Pearl River
Covington
Slidell
Talisheek
Blond
Sheridan
Geismar
St. James
Larose
Gibson
BR Simulcast
BR
Central
LSU
WBR
Hammond
Gray
Berwick
Baywood
Ramah
Sage Hill
Parker Road
Iberville
Livingston
Jackson
Greensburg
Superdome
South Baton Rouge
Baldwin
Pointe Coupee
Theriot
Paincourtville
Boothville
Mobile Units
94
96
97
98
99
100
Denham Springs
Clinton
St. George
Zone 1: 43 Sites in Full Operation

## Slide 5: Zone 2: 18 Sites in Full Operation
N. Simulcast
Gretna
Galleria
NO East
Houma
Lafitte
Bayou Gauche
Hahnville
St. Rosalie
Kenner
Airport
Port Fourchon
Reggio
Montegut
Bourg
Buras
Wilmer
Grand Isle
Thibodeaux

## Slide 6: Zone 3: 55 Sites in Full Operation
Clearwater
Monroe
Winnfield
Delhi
Chopin
Dry Prong
Hagewood
Bossier(City)
Farmerville
Minden
Natchitoches
Bastrop
Greenwood
Ruston
Hineston
Ashland
Vivian
Newellton
Noble
Transylvania
Alexandria
Avoyelles
Bellevue
Bernice
Calhoun
Columbia
Ferriday
Homer
Jena
Jonesboro
Mansfield
Many
Marion
Oak Grove
Plain Dealing
Ringgold
Sentell
Tallulah
Wheeling
Shreveport
West Monroe
Chase
Keachi
Coushatta
Shongaloo
Sibley
Vick
Calvin
Arcadia
Enterprise
Holloway
Chatham
Cypress
Logansport
Pelican

## Slide 7: Zone 4: 34 Sites in Full Operation
Abbeville
Acadia
Arsene LeBleu
DeQuincy
Dry Creek
Jeanerette
Jennings
Johnson Bayou
Lafayette
Lake Charles
Leesville
Merryville
Opelousas
Parks
Rockefeller
Rosepine
Scott
Sulphur
Vermillion
Ville Platte
Vinton
Craven
Hicks
Hornbeck
Oakdale
Roseland
E. Jennings
Anacoco
Oberlin
Moss Bluff
New Iberia
Eunice
Starks
Bell City

## Slide 8: Channel Summary
Total Channels 1343
1292 Channels on 149 Sites
51 Channels on 6 Mobile Sites

## Slide 9: System Statistics

## Slide 10
SUBSCRIBERS

## Slide 11: PUSH TO TALK

## Slide 12: PUSH TO TALK PER DAY

## Slide 13: BUSIES

## Slide 14: Top Busy Sites
Gray 172
Denham Springs 158
Thibodaux 44

## Slide 15
SITE OUTAGES
Total Downtime: 3432 Hours
Abbeville | Acadia | Alexandria | Arcadia | Ashland
Avoyelles | Bayou Gauche | Baywood | Bellevue | Berwick
Blue | Bootheville | Bossier | Bridge City | Calhoun
Calvin | Chopin | Clearwater | Clinton | Coushatta
Denham Springs | Dry Creek | Dry Prong | Enterprise | Farmerville
Geismar | Gibson | Gray | Green | Greensburg
Greenwood | Hagewood | Hineston | Holloway | Homer
Hornbeck | Iberville | Jackson | Jeanerette | Jennings

## Slide 16
SITE OUTAGES
Total Downtime: 3432 Hours
Johnson Bayou | Keachi | Lake Charles | LaPlace | Larose
Leesville | Mansfield | Monroe | Montegut | Newellton
Oak Grove | Opelousas | Paincourtville | Pan Am | Parker Road
Parks | Pointe Coupee | Port Fourchon | Ringgold | Rockefeller
Sage Hill | Scott | Sentell | Sheridan | South Baton Rouge
St. George | St. James | Superdome | Tallulah | Theriot
Trailer 100 | Trailer 99 | Vermilion | Vick | Ville Platte
Vinton |  |  |  | 

## Slide 17
SITE OUTAGE DATA
69%
Chart: 
| Telco | Power | Equipment
What were the issues? | 0.84 | 0.05 | 0.11

## Slide 18: SYSTEM STATISTICS
Chart: Percentage of ALL SITES in WIDE AREA Operations
| July | August | September | Avg. Uptime
Series 1 | 0.9903 | 0.9894 | 0.9878 | 0.9891
Column1
Column2

## Slide 19: Subscriber Statistics
Agencies
614
Security Groups
192
Talkgroups
6,597

## Slide 20: Agencies Added Last 3 Months
Louisiana office of museums police Department
Pelican ambulance

## Slide 21: System Coverage

## Slide 22
Present Coverage

## Slide 23: Questions?

## Slide 24: Ethernet Update

## Slide 25: Existing Network

## Slide 26: New LWIN Network

## Slide 27: Completed Sites
Deployment Status Schedule
Deployment Date(s) | Phase | Site | Progress | Zayo Status | Motorola Cutover Completed | Cradlepoint Installed | Antenna Installed
5/10/2023 | HUB | Zone 1 - Baton Rouge | 100% | Complete | Yes | N/A | N/A
6/1/2023 | HUB | Zone 2 - Gretna | 100% | Complete | Yes | N/A | N/A
5/30/2023 | HUB | Zone 3 - Alexandria | 100% | Complete | Yes | N/A | N/A
5/11/2023 | HUB | Zone 4 - Baton Rouge | 100% | Complete | Yes | N/A | N/A
7/21/2023 | Pilot | Denham Springs | 100% | Complete | Yes | Yes | Yes
10/27/2023 | Pilot | Baywood | 100% | Complete | Yes | Yes | Yes
11/2/2023 | Pilot | Jackson | 100% | Complete | Yes | Yes | Yes
02/26/24 and 02/29/24 | Deployment | Sage Hill - Tower | 100% | Complete | Yes | Yes | Yes
02/28/24 and 03/15/24 | Deployment | Eunice - Tower | 100% | Complete | Yes | Yes | Yes
3/12/2024 | Deployment | Kenner Dispatch - Console | 100% | Complete | Yes | Yes | Yes
2/26/2024 | Deployment | Vernon EOP - Console (CP Only) | 100% | Complete | Yes | Yes | No - No Antenna Needed
03/05/24 and 04/02/24 | Deployment | Delhi - Tower | 100% | Complete | Yes | Yes | Yes
4/30/2024 | Deployment | Ponchatoula PD (Console) | 100% | Complete | Yes | Yes | Yes
03/05/24 | Deployment | LWIN - TRANSYLVANIA (MON) - Tower | 100% | Complete | Yes | Yes | Yes
03/07/24 03/26/24 | Deployment | LWIN - SENTELL (Tower) | 100% | Complete | Yes | Yes | Yes
03/26/24 | Deployment | LWIN - SIBLEY (SHRV) - Tower | 100% | Complete | Yes | Yes | 
03/27/24 | Deployment | LWIN - NEW IBERIA - Tower | 100% | Complete | Yes | Yes | Yes
03/27/24 | Deployment | LWIN - NEW IBERIA - Console | 100% | Complete | Yes | Yes | 
04/02/24 | Deployment | LWIN - MANY (PTP) - Tower | 100% | Complete | Yes | Yes | Yes
06/11/24 | Deployment | LWIN - Troop I - Console | 100% | Complete | Yes | Yes | No - No Antenna Needed
06/11/24 | Deployment | LWIN - VICK - Tower | 100% | Complete | Yes | Yes | No - No Antenna Needed

## Slide 28: Completed Sites
Deployment Status Schedule
Deployment Date(s) | Phase | Site | Progress | Zayo Status | Motorola Cutover Completed | Cradlepoint Installed | Antenna Installed
06/12/24 | Deployment | LWIN - POINTE COUPEE SO - Tower | 100% | Complete | No Need to confirm if a circuit is in place at the tower and console site in order to proceed with the migration. | Yes | No - No Antenna Needed
06/13/24 | Deployment | LWIN - HAGEWOOD (PTP) - Tower | 100% | Complete | Yes | Yes | Yes
06/13/24 | Deployment | LWIN GREENWOOD (SHRV) - Tower | 100% | Complete | Yes | Yes | No - No Antenna Needed
02/28/24 | Deployment | LWIN - St. Landry Sheriff Office (Console) | 100% | Complete | Yes | Yes | Yes
06/18/24 | Deployment | LWIN - HICKS (PTP DHDC) - Tower | 100% | Complete | Yes | Yes | Yes
06/18/24 | Deployment | LWIN - Jefferson Davis SO - Console | 100% | Complete | Yes | Yes | No - No Antenna Needed
06/20/24 | Deployment | LWIN - CALHOUN (MON) - Tower | 100% | Complete | Yes | Yes | Yes
06/20/24 | Deployment | LWIN - ARCADIA (SHRV) - Tower | 100% | Complete | Yes | Yes | No - No Antenna Needed
07/02/24 | Deployment | WEST MONROE (MON) - Tower | 100% | Complete | Completed on Fiber - #INC1312656 | Yes | No
07/02/24 | Deployment | LWIN - BERNICE (MON) - Tower | 100% | Complete | Yes | Yes | Yes

## Slide 29: Completed Sites
Deployment Status Schedule
Pending Motorola Cutover Date |  |  |  |  |  |  | 
06/25/24 | Deployment | LWIN - BELLEVUE (SHRV) - Tower | 100% | Complete | Yes | Yes | No
06/26/24 | Deployment | LWIN - PAINCOURTVILLE (NO) - Tower | 90% | Pending | Activation Scheduled on August 5 | Yes | No
07/09/24 | Deployment | LWIN - HORNBECK (PTP) - Tower | 50% | Pending | Yes | Yes | No
07/09/24 | Deployment | LWIN - NOBLE (SHRV) - Tower | 100% | Complete | Yes | Yes | No
07/10/24 | Deployment | LWIN - COUSHATTA (SHRV) - Tower | 100% | Complete | Yes | Yes | Yes
07/10/24 | Deployment | LWIN - KEACHI - Tower | 100% | Complete | Yes | Yes | Yes
07/11/24 | Deployment | LWIN - Union 911 - Console | 100% | Complete | Yes | Yes | No

## Slide 30: Completed Sites
Deployment Status Schedule
Deployment Date(s) | Phase | Site | Progress | Status | Risks, Issues, Dependences or Concerns | Motorola Cutover Completed | Cradlepoint Installed | Antenna Installed | Alternate Antenna Solution Needed
TBD | Deployment | ST. James | 0% | On-Hold | ** CP SHIPPED TO ATT/BLAINE FOR TESTING PURPOSES. PENDING CIRCUIT DELIVERY CONFIRMATION AND ANTENNA INSTALLATION | No | No | No | 
TBD | Deployment | Troop E Dispatch - Console | 0% | On-Hold | ATT circuit released to the customer on 01/22/24, Zayo pending customer to advise when site will be ready to deploy. | No | No | No | 

## Slide 31: BATCH 3 SITES AND SITE TYPES
TROOP I DISPATCH CONSOLE
POINTE COUPEE SO CONSOLE
JEFFERSON DAVIS SO CONSOLE
BERWICK TOWER
WINNFIELD TOWER
CHOPIN TOWER
HAGEWOOD TOWER
MINDEN TOWER
GREENWOOD TOWER
ASHLAND TOWER
NEWELLTON TOWER
BELLEVUE TOWER
CALHOUN TOWER
WHEELING TOWER
CALVIN TOWER
ARCADIA TOWER
HICKS/LEESVILLE TOWER
HORNNBECK TOWER
OAKDALE TOWER
ROSELAND TOWER

## Slide 32: BATCH 4 SITES AND SITE TYPES
BOSSIER CITY PD CONSOLE
BOSSIER CITY FD CONSOLE
UNION PARISH 911 CONSOLE
TANGIPAHOA EOC TBD
POINTE COUPEE TOWER
MONROE TOWER
BOSSIER CITY TOWER
FARMERVILLE TOWER
BASTROP TOWER
VIVIAN TOWER
NOBLE TOWER
BERNICE TOWER
COLUMBIA TOWER
HOMER TOWER
JONESBORO TOWER
MANSFIELD TOWER
MARION TOWER
OAK GROVE TOWER
PLAIN DEALING TOWER
RINGGOLD TOWER
WEST MONROE TOWER
CHASE TOWER
COUSHATTA TOWER
SHONGALOO TOWER
CHATHAM TOWER
KEACHI TOWER

## Slide 33: BATCH 5 SITES AND SITE TYPES
AVOYELLES 911 CONSOLE
BAKER PD CONSOLE
TROOP C CONSOLE
BRIDGE CITY TOWER
SHERIDAN TOWER
GRAY TOWER
PARKER RD TOWER
BALDWIN TOWER
GIBSON TOWER
BOOTHVILLE TOWER
HOLLOWAY TOWER
ABBEVILLE TOWER
ACADIA TOWER
JEANERETTE TOWER
LAFAYETTE TOWER
CLINTON TOWER
ST. ROSALIE TOWER
BURAS TOWER
BAYOU GAUCHE TOWER
MONTEGUT TOWER
BOURG TOWER
DRY PRONG TOWER
NATCHITOCHES TOWER
FERRIDAY TOWER
ENTERPRISE TOWER
LAKE CHARLES TOWER
LEESVILLE TOWER
OPELOUSAS TOWER
EAST JENNINGS TOWER
ANACOCO TOWER

## Slide 34: BATCH 6 SITES AND SITE TYPES
MONROE PD CONSOLE
PLAQUEMINES SO CONSOLE
LINCOLN SO CONSOLE
LAFOURCHE 911 CONSOLE
POINTE COUPEE SO CONSOLE
RUSTON PD CONSOLE
ST. GEORGE TOWER
HAHNVILLE TOWER
RUSTON TOWER
ALEXANDRIA TOWER
AVOYELLES TOWER
JENA TOWER
DEQUINCY TOWER
VINTON TOWER
OUACHITA TOWER
THIBODAUX TOWER
CALCASIEU SO TOWER
HINESTON TOWER

## Slide 35: Thank You!