## Slide 1: Project Management

## Slide 2: Purpose
To make Subgrantees aware of the scope + contracts + cost reasonableness of procuring Project Management + Architectural/Engineering (A/E) services so that they can receive/keep the maximum Federal dollars.

## Slide 3: Authorities
44 Code of Federal Regulations (CFR) Part 206
Hazard Mitigation Assistance (HMA) Unified Guidance July 12, 2013
OMB Circular 133
FEMA 322 – Public Assistance Guide July 2007

## Slide 4: Acronyms
A/E Architectural/Engineering
CA Construction Administration
CEF Cost Estimating Format
CM Construction Management
FIPS Federal Information Processing System
FP+C Louisiana Office of Facility Planning + Control
GA Grant Administration

## Slide 5: Acronyms (Continued . . . )
HMA Hazard Mitigation Assistance
PM Project Manager/Management
RFI Request for Information
RFP Request for Proposal
RFQ Request for Qualifications
SOV Schedule of Values
SOW Scope of Work

## Slide 6: 3 things to be aware of
Project vs. construction management vs. grants administration.
Reasonable fee curves for Architectural/Engineering (A/E) services?
Cost analysis.

## Slide 7: Project vs. Construction Management vs. Grants Administration

## Slide 8: Project Management (PM) Define
The oversight of an eligible project from the design phase to the completion of the work. (Source: Disaster Assistance Policy [DAP] 9525.6)

## Slide 9: Project Management (PM) Define (Continued . . . )
Eligible PM activities are those activities that the Subgrantee would have performed in the absence of Federal funding.

## Slide 10: PM activities
Direct management of projects in the concept + design stages.
Procurement activities for architectural/engineering services + performance of work.

## Slide 11: PM activities (Continued . . . )
Review + approval of the project design.
Oversight of project work by both A/E and construction contractors.

## Slide 12: Grants Administration (GA) Define
Activities necessary to apply for, administer and closeout a grant.

## Slide 13: GA activities
Application process.
Reimbursement activities.
Quarterly Report preparation.
Grant reconciliation activities.

## Slide 14: Construction Management (CM) Define
Also known as Construction Administration (CA)/Construction Management (CM), usually performed by the A/E contractor/firm as part
of their basic services during the phase of construction.

## Slide 15: CA/CM activities
Preparation of construction documents, based on final design, for procurement of bids.
Bid tab analysis + recommendation.

## Slide 16: CA/CM activities (Continued . . . )
Periodic supervision of construction:
  Such as weekly progress meetings + processing contractor’s pay applications + respond to requests for information (RFI) + preparation of change orders (as necessary) + etc.

## Slide 17: Do NOT overlap PM + CA/CM

## Slide 18
Construction oversight
Procurement Activities
  Construction Contract
Kickoff meeting
Quarterly Reports
Schedule work plan + budget
Other
Where overlap may occur . . .

## Slide 19: For example . . .

## Slide 20: How to avoid overlap
Clearly distinguish roles and responsibilities for activities that have the same title but not the same work.
Well-defined contracts.
Other.

## Slide 21: Overlap can lead to . . .
Request for an explanation.
  Requires distinct narrative separating two (2) activities under the same category.
Withholding/de-obligation of funds.

## Slide 22: Reasonable fee curves for A/E services?

## Slide 23: 2 fee curves
FEMA fee curves A + B.
Louisiana Office of Facility Planning + Control (FP&C) curve.

## Slide 24: Curves A + B
Curve A - Above average complexity.
Curve B - Average complexity.

## Slide 25: Curve A
Applies to projects of above-average complexity and nonstandard design:
  Airports with extensive terminal facilities.
  Water + wastewater + industrial waste treatment plants.
  Hospitals + schools + office buildings.
  Power plants.
  Highway + railway tunnels.
  Pumping stations.
  Incinerators.
  Complicated waterfront + marine terminal facilities.

## Slide 26: Curve A (Continued . . . )
CURVE A. COMPENSATION FOR BASIC SERVICES EXPRESSED AS A PERCENTAGE OF CONSTRUCTION COST FOR PROJECTS OF ABOVE-AVERAGE COMPLEXITY AND NON-STANDARD DESIGN

## Slide 27: Curve B
Applies to projects of average complexity:
  Industrial buildings + warehouses + garages + hangars + comparable structures.
  Bridges + other structures of conventional design.
  Simple waterfront facilities.
  Roads + streets.
  Conventional levees +
  floodwalls + retaining walls.
  Small dams.
  Storm sewers + drains.
  Sanitary sewers.
  Water distribution lines.
  Irrigation works (except pumping plants).
  Airports (except as classified for Curve A).

## Slide 28: Curve B (Continued . . . )
CURVE B. COMPENSATION FOR BASIC SERVICE EXPRESSED AS A PERCENTAGE OF CONSTRUCTION COST FOR PROJECTS OF AVERAGE COMPLEXITY

## Slide 29: FP&C Fee Curve
Simple
Average
Medium complex
Complex

## Slide 30: Fee curve adjustments Other FP&C factors
Adjustment for renovations.
Repetitive or duplicative work.
Prefabricated building.
Multiple projects in a single contract:
  Fee based on sum of the projects.
Segregate projects:
  Fee based on respective portions.

## Slide 31: Fee adjustment (FP&C) Change in project value: Pre-bid
Typically no adjustment for small project cost change.
Large changes in project cost may warrant fee adjustment:
  Change in scope-based cost.
  Original estimate significantly under or over valued.

## Slide 32: Fee adjustment Change orders
A/E fee adjustments are appropriate based on changes in costs during construction.
  A/E fee adjustments are eligible for FEMA reimbursement provided the change order is deemed eligible by FEMA.
  Cost overruns may be the responsibility of the Subgrantee based upon availability of funds.

## Slide 33: Fee adjustment FP&C change order guidance
Change orders resulting from errors + omissions . . .
  Generally do not warrant
  fee adjustment.

## Slide 34: What to look for when reviewing a contract

## Slide 35: PM contracts
Procurement:
  Must be procured through a request for proposal (RFP) with two (2) or more bids.
Contract should include:
  Schedule (start + end date).
  Budget (include a not to exceed clause).
  Scope of work (SOW).
  Payment schedule.

## Slide 36: A/E contracts
Procurement:
  Procured through a request for qualifications (RFQ).
    BEST PRACTICE: Specify in the RFQ that fees will be based on FEMA or FP&C curve.

## Slide 37: A/E contracts (continued . . .)
Contract should include:
  Schedule (start + end date).
  SOW.
  Milestones/payment schedule.
  Additional services.
    May require cost analysis to determine reasonableness.

## Slide 38: Cost Analysis

## Slide 39: What is procurement?
Process of acquiring (buying, purchasing, renting/leasing) goods + services.

## Slide 40: How is procurement regulated?
44 CFR 13.36 Promotes equal opportunity. Promotes cost-effective acquisition.

## Slide 41: Why is procurement important?
FEMA must hold Grantees and Subgrantees accountable for non-compliance with Federal procurement practices.
May disallow all or part of contracts that are NOT in compliance.
Subject to de-obligation of Federal funds.

## Slide 42: What is a cost analysis?
A Subgrantee’s demonstration that the cost of an acquisition is reasonable:
  It is the “story” of a Subgrantee’s procurement.
  An analytical explanation of why the procurement decisions were reasonable.

## Slide 43: Why must a cost analysis be performed?
Because it is REQUIRED by 44 CFR 13.36 (f)(1).

## Slide 44: When is a cost analysis required?
If procuring with Federal funds, cost analysis must be performed:
  Non-competitive procurement.
  Sole source contract.
  For all scope alignments.
  For all contract amendments.
  For all change orders.

## Slide 45: What is “cost reasonableness”?
A cost that is both fair + equitable for the type of work performed. (OMB A-87)

## Slide 46: How is cost reasonableness determined?
Using comparisons, which might include:
  Historic data for cost of similar work.
  Average costs for similar work in the same market.
  Catalogs.
  Internet.

## Slide 47: How is cost reasonableness determined? (Continued . . . )
Using cost comparisons, which might include:
  Published unit costs from nationally – or industry – recognized cost standards like RSMeans, BNi Costbooks, Marshal & Swift and others.

## Slide 48: How complex does a cost analysis need to be?
The method + degree of analysis depends on the facts surrounding each procurement.

## Slide 49: Is a specific format required?
No specific format is required.
A sample cost analysis has been provided that follows the process outlined in this presentation.

## Slide 50: Cost analysis process: 9 key steps
1. Identify the who, what, when, where and why:
  Person preparing analysis and date prepared.
  Grantee/Subgrantee and Federal Information Processing System (FIPS)/Applicant ID number.

## Slide 51: Cost analysis process (Continued . . . )
  1. Identify the who, what, when, where and why: (Continued . . . )
  Project title.
  Address and facility being analyzed (if applicable).

## Slide 52: Cost analysis process (Continued . . . )
  1. Identify the who, what, when, where and why: (Continued . . . )
  Project numbers and amendments.
  Cost analyzed (using contracts, estimates, invoices, etc.).

## Slide 53: Cost analysis process (Continued . . . )
2. Describe the party requesting the cost analysis and intended purpose:
  Include relevant background information.
3. Describe the key points of the cost analysis:
  Define the costs expended by the Subgrantee that require cost analysis.

## Slide 54: Cost analysis process (Continued . . . )
4. Define the type of procurement:
  Describe intention to acquire. Break down how much individual parts of the project will cost (lump sum, unit price, etc.).
  Explain how those costs correspond with the project’s cost.

## Slide 55: Cost analysis process (Continued . . . )
5. Identify the methods to justify the cost estimation:
  There are many different methods of comparison that can be used to establish cost reasonableness including, but not limited to, pre-disaster price for similar work or average cost for similar work in the same market.

## Slide 56: Cost analysis process (Continued . . . )
6. Explain the ways in which the selected comparables are alike:
  Adjust the data to account for any relevant differences such as:
    Inflation/time value of money (Consumer price index [CPI]).
    Price volatility and raw materials.
  Compare adjusted costs with the project costs.

## Slide 57: Cost analysis process (Continued . . . )
7. Conclusion:
  Is the cost reasonable or not?
  If the project cost is within 10% of the adjusted cost then it is reasonable.

## Slide 58: Cost analysis process (Continued . . . )
8. Recommendation (if applicable):
  If the cost is determined to be reasonable, and depending on what purpose the cost analysis is being performed for, make a recommendation about the desired outcome.

## Slide 59: Cost analysis process (Continued . . . )
9. Last but not least, provide references and citations to document all cost analyses.
Back up! Back up! Back up!

## Slide 60: Proper procurement can minimize cost analysis requirements
Procuring properly does not eliminate the need for cost analysis, but . . .
  GOHSEP/FEMA may view a properly procured contract with an adequate number of responses as sufficient.

## Slide 61: Sole source/ non-competitive procurement

## Slide 62: What about sole source or non-competitive procurement?
Cost analysis is still required.
To be approved, must meet the specific requirements in 44 CFR 13.36(d)(4)(i) A-D.

## Slide 63: What about sole source or non-competitive procurement? (Continued . . . )
Sole source/non-competitive cost analysis are difficult:
  Acceptability is determined on a case-by-case basis by GOHSEP/FEMA.
  Compelling narrative required.
  Previous transactions from sole source vendor may be the only option.

## Slide 64: Contact
Unmesh Kirtikar
unmesh.kirtikar@la.gov
Jeffrey Giering
jeffrey.giering@la.gov
Tenesha Wilson
tenesha.wilson@la.gov

## Slide 65: Questions?

## Slide 66: For more information + to download materials from today’s seminar:
gohsep.la.gov/outreach.aspx