## Slide 1: Hazard Mitigation Planning + Your Community

## Slide 2: Hazard Mitigation Planning + Your Community
A Hazard Mitigation Plan (HMP) is required for your community to receive FEMA hazard mitigation funding.

## Slide 3: Authorities
Robert T. Stafford Disaster Relief and Emergency Assistance Act (Stafford Act)
44 Code of Federal Regulations (CFR) Part 201
44 CFR Part 206

## Slide 4: Acronyms
APA Approved Pending Adoption
HIRA Hazard Identification Risk Assessment
SDMI Stephenson Disaster Management Institute
THIRA Threat and Hazard Identification Risk Assessment

## Slide 5: Why they are important to you
State + local + Federally recognized Tribal governments are required to develop a HMP as a condition for receiving certain types of grant funding:
Hazard Mitigation Grant Program (HMGP)
Pre-Disaster Mitigation (PDM) Grant Program
Flood Mitigation Assistance (FMA) Program

## Slide 6: Who needs a plan?
Jurisdictions who own property AND . . .
Have governing authority over the property.

## Slide 7: Do I need my own plan?
Yes, if you’re a Parish.
If you are NOT a Parish, we encourage you to be a participating jurisdiction within the Parish-level plan.

## Slide 8: Participating jurisdiction
Provide input + attend meetings.
Provide a point of contact (POC).
Participate in risk assessment development + individual risk assessment.
Adopt the plan.

## Slide 9
Parish Hazard Mitigation Plan Expiration Dates
Parish plans have a
5-year update cycle.

## Slide 10: If you’re building your own plan, here are some things to know . . .

## Slide 11: 10 steps of a 12-month timeline
Develop a Planning Process.
Complete a Risk Assessment.
Conduct a Mitigation strategy meeting.
Address plan maintenance.
Convene a draft review meeting.

## Slide 12: 10 steps of a 12-month timeline (Continued . . . )
GOHSEP review.
FEMA review.
Obtain Approval Pending Adoption (APA) status from FEMA.
Resolution signed.
FINAL approval from FEMA.

## Slide 14: Plan development . . .
State-assisted (SDMI) . . .
You . . .
Or a Parish contractor?

## Slide 15: Choosing a contractor
Follow proper procurement guidelines.
  MUST be competitively bid.

## Slide 16
Initial meeting with planning team + stakeholders to:
  Explain planning process.
  Decide on timeline.
  Define participation roles + responsibilities.

## Slide 17
Determine the planning area + resources.
Build the planning team.
Create an outreach strategy to stakeholders.

## Slide 18
Each jurisdiction in the Plan must:
  Identify hazards.
  Profile hazards.
  Determine vulnerability + impact.

## Slide 19: Identify hazards
Describe all natural hazards that effect the jurisdictions in the planning area.
  Flood
  Hurricane
  Tornado
  Winter storm
  Thunderstorms
  Coastal land loss
  Storm surge
  Subsidence
  Wildfire
  Dam failure
  Levee failure

## Slide 20: Profile hazards
Location.
Extent.
Previous occurrences.
Probability of future occurrences.

## Slide 21: Determine vulnerability + impact
Vulnerability
  Demonstrated through past occurrences.
  Characteristics of the community’s assets that make jurisdictions susceptible to damage.
Impact
  Consequences or effects of past occurrences on the community assets.

## Slide 22: HIRA vs. THIRA
Hazard Identification Risk Assessment (HIRA):
  Natural hazards.
  Location + extent.
  Previous occurrences + probability of future occurrences.

## Slide 23: HIRA vs. THIRA (Continued . . . )
Threat + Hazard Identification + Risk Assessment (THIRA):
  Technological + human caused threats
  Capability a jurisdiction has to respond to a natural or manmade threat event.

## Slide 24
Blueprint for mitigation disaster losses
State goals:
  Improve education + outreach efforts.
  Improve data collection . . .
Possible actions:
  HM workshops.
  Mitigation projects.
  Other . . .
Prioritize actions to guide how you implement funding.

## Slide 25: Remember . . .
PROJECT FUNDING is ONLY available if the action is in the Plan.

## Slide 26
The plan is a living document.
  Monitor
  Evaluate
  Update/amend

## Slide 27
Planning Team
Stakeholders
Public
Comment period

## Slide 28
Submit DRAFT to GOHSEP for review:
  PIVOT DATE (6 months before expiration).

## Slide 29
submits to FEMA.
has a 45-day review period.

## Slide 30
Plan receives APA status from FEMA.

## Slide 31
All participating jurisdictions must sign the resolution page.

## Slide 32
Plan must be adopted by all participating jurisdictions to receive final approval from FEMA.

## Slide 33: Secure planning grant funding
Hazard Mitigation Grant Program (HMGP) + Pre-Disaster Mitigation (PDM) can fund complete plan development.
Flood Mitigation Assistance (FMA) can only fund flood portion of plan development.
Post-disaster
Non-disaster
Non-disaster

## Slide 34: Remember . . .
No Hazard Mitigation Plan.
No grant funding.

## Slide 35: Contact
Brenda Cooper
brenda.cooper@la.gov
Jeffrey Giering
jeffrey.giering@la.gov
Nicolette English
nicolette.english@la.gov

## Slide 36: Questions?

## Slide 37: For more information + to download materials from today’s seminar:
gohsep.la.gov/outreach.aspx